KEMPER DESIGN SERVICES

Welcome to the Team

Apex Regenerative Hair Center

Prepared by Damian Kemper  |  Kemper Design Services  |  April 2025

Dr. Faruqi,

Thank you for choosing Kemper Design Services. I am genuinely excited to build something impactful for Apex Regenerative Hair Center. This welcome packet covers everything you need to know as we kick off — your project overview, my contact information, what happens each week, and how we will work together to make this a smooth and successful engagement.

If you have any questions at any point, do not hesitate to reach out. My goal is to keep you informed, deliver on time, and build a system you and your team will rely on for years.

Let's get to work.

Damian Kemper

Owner — Kemper Design Services

kemperdesignservices@gmail.com

01  Your Project at a Glance

Here is a high-level summary of your four-stage AI system build. Each stage builds on the one before it and delivers a concrete, working piece of the system.

| Stage | What Gets Built | Timeline | Payment |
| --- | --- | --- | --- |
| Stage 1 — Foundation | Twilio number, Retell AI agent connection, Google Calendar setup, call routing | Week 1 | $2,375 — due on signing |
| Stage 2 — AI Intake & Autoscheduler | Full AI conversation flow, intake collection, real-time availability checking and booking | Week 2 | $2,375 — due Week 2 start |
| Stage 3 — Integrations & Automation | Google Sheets lead logging, SMS/email confirmations, staff notifications, AI summaries | Week 3 | $2,375 — due Week 3 start |
| Stage 4 — Website Booking & Launch | Book Consultation button, embedded Cal.com page, UTM tracking, final QA and handoff | Week 4 | $2,375 — due on delivery |

02  Your Point of Contact

| YOUR PROJECT LEAD Damian Kemper Owner — Kemper Design Services kemperdesignservices@gmail.com |  | RESPONSE TIME COMMITMENTS Email — within 1 business day Urgent issues — same business day Preferred channel: Email |
| --- | --- | --- |

| Important | For the fastest response, please email kemperdesignservices@gmail.com with a clear subject line describing your question or concern. This creates a written record and ensures nothing falls through the cracks. |
| --- | --- |

03  What Happens Next — Week by Week

Here is exactly what will happen each week of the engagement, and what I will need from your team to keep everything on track.

| Week 1 | Kemper Design Services - Set up and configure your Twilio phone number and call routing - Connect Retell AI agent to Twilio via SIP - Configure Google Calendar (working hours, buffer times, event types) - Build and test basic call answering and fallback transfer logic - Deliver initial system test for your review | What We Need From You - Complete and return the Client Access Request form - Confirm your business phone number and fallback number - Confirm your calendar working hours and consultation duration - Designate one internal point of contact for this project - Review and approve the initial call routing test |
| --- | --- | --- |

| Week 2 | Kemper Design Services - Build the full Madison AI conversation flow (intake, booking, confirmation) - Program all required intake fields into the agent - Connect Retell AI to Google Calendar for real-time availability checking - Build and configure automatic appointment booking logic - Test end-to-end call flow and iterate based on your feedback | What We Need From You - Review and approve the AI conversation script draft - Provide any custom FAQs or services you want Madison to know - Test a live call and provide feedback within 2 business days - Confirm the exact service types to offer (e.g., hair restoration consultation) |
| --- | --- | --- |

| Week 3 | Kemper Design Services - Build Google Sheets lead logging (one row per call, all fields) - Set up SMS confirmation messages via Twilio - Set up email confirmation to patients and staff notification emails - Configure AI call summary and lead status tracking - Test all integrations end-to-end | What We Need From You - Confirm the email address(es) for staff notifications - Review and approve the SMS confirmation message text - Review the Google Sheet structure and confirm column layout - Respond to any integration questions within 2 business days |
| --- | --- | --- |

| Week 4 | Kemper Design Services - Build and embed the website booking button (Cal.com integration) - Configure Cal.com event types and connect to Google Calendar - Set up UTM tracking for website booking source attribution - Conduct final QA across all system components - Deliver handoff documentation, training guide, and user guide | What We Need From You - Provide website access (WordPress/CMS credentials) for button installation - Review and approve the final system before launch - Ensure front desk staff have reviewed the training guide - Confirm go-live date and approve final launch |
| --- | --- | --- |

04  What We Need From You

To keep the project on schedule and avoid delays, I need three things from your team:

| 01 | Return the signed Client Access Request form within 3 business days of receiving it. This gives me the credentials I need to begin building. |
| --- | --- |
| 02 | Respond to questions and review requests within 2 business days. Delays in your response will delay your delivery date. |
| 03 | Designate one internal point of contact. All project communications should flow through a single person on your team to keep things efficient. |

05  How to Give Feedback

Requesting Changes

Email me at kemperdesignservices@gmail.com with a clear description of the change you are requesting. Please include the specific section or component you want changed, and what you would like it to do instead.

What Is In Scope

- Changes to the AI conversation wording or tone

- Adding or removing service types from the agent

- Adjusting business hours, buffer times, or slot duration

- Updating confirmation message text

- Minor additions to the Google Sheet column layout

What Requires a Change Order

- Adding a new platform or integration not in the original scope

- Building a second AI agent or call flow for a different purpose

- Custom reporting dashboards or CRM software integrations

- Multilingual support or additional language configurations

- Major redesign of the booking flow or patient journey

| Change Orders | Any out-of-scope work requires a written change order with agreed pricing before work begins. I will always give you a clear estimate and get your approval before proceeding. |
| --- | --- |

06  Project Milestones & Payment

Payment is tied directly to delivery — you pay when I deliver. Here is a friendly reminder of the four milestone payments:

| Milestone | Trigger | Amount |
| --- | --- | --- |
| Stage 1 Deposit | Upon signing this agreement | $2,375 |
| Stage 2 Payment | Week 2 build begins | $2,375 |
| Stage 3 Payment | Week 3 build begins | $2,375 |
| Stage 4 Final | Delivery and launch approval | $2,375 |

| Monthly Maintenance | After your system launches, Kemper Design Services offers ongoing monthly maintenance for $49.99/month. This covers 24/7 monitoring, monthly AI performance reviews, minor script adjustments, and priority support. This is entirely optional and can be cancelled with 30 days notice. |
| --- | --- |

I am honored to be your partner on this project. Let's build something exceptional together.

Questions? Reach out anytime: kemperdesignservices@gmail.com